## Sheet1
Notifictn type | Main WorkCtr | Notification | Created on | Completn date | Priority | Priority | PriorityType | Order | Sort field | Description | Created by | Description | Reported by | System status
M1 | GKEST | 10199498 | 2016-10-21 | 2017-01-22 | 5 | Low | PM | 10115899 |  | Move bio reader and telephone | COULOMBEM |  | COULOMBEM | NOCO ORAS
M1 | GKEST | 10203345 | 2016-11-14 | 2016-11-20 | 3 | High | PM | 10116573 | 2300-CMP-268 | Airport camera is off-line | MELVINB | CAMERA, P10268 Airstrip PTZ | B. MELVIN | NOCO ORAS
M1 | GKEST | 10207412 | 2016-12-09 | 2016-12-17 | 2 | HIGH-Within 2 Weeks | P1 | 10117406 | 3400-BRD-016 | 3rd Floor Bio - reader not working | MELVINB | READER, Bio, IN, 3F Virtual Barrier | B. MELVIN | NOCO ORAS
M1 | GKEST | 10207838 | 2016-12-12 | 2017-02-07 | 2 | HIGH-Within 2 Weeks | P1 | 10117408 | 3400-BRD-017 | Bio-reader not working | MELVINB | READER, Bio, IN, 4F Virtual Barrier | B. MELVIN | NOCO ORAS
M1 | GKEST | 10208191 | 2016-12-13 | 2017-01-06 | 2 | HIGH-Within 2 Weeks | P1 | 10117415 |  | Red entrance sequence not working | MELVINB |  | B. MELVIN | NOCO ORAS
M1 | GKEST | 10212902 | 2016-12-31 |  | 4 | LOW-Opportunistic | P1 |  | 3400-CMF-017 | Camera is dirty | MELVINB | CAMERA, F30017 Exp Bay Ext Entrance | B. MELVIN | OSNO
M1 | GKEST | 10212903 | 2016-12-31 |  | 3 | MEDIUM-Within 1 Mnth | P1 |  | 3400-CMF-128 | Dirty inside camera housing | MELVINB | CAMERA, F32128 Srt Hse Grse Blt GBx In 1 | B. MELVIN | OSNO
M1 | GKEST | 10212905 | 2016-12-31 |  | 4 | LOW-Opportunistic | P1 |  | 3810-CMF-202 | Camera is dirty | MELVINB | CAMERA, F20202 Proc Plant Emer Exit D7 | B. MELVIN | OSNO
M1 | GKEST | 10212906 | 2016-12-31 |  | 4 | LOW-Opportunistic | P1 |  | 3810-CMF-203 | Camera is dirty | MELVINB | CAMERA, F20203 Proc Plant Emer Exit D6 | B. MELVIN | OSNO
M1 | GKEST | 10212907 | 2016-12-31 | 2017-01-06 | 4 | LOW-Opportunistic | P1 | 10117975 | 3300-CMF-228 | Camerqa is out of focus | MELVINB | CAMERA, F20228 Fines DMS Underflow NW | B. MELVIN | NOCO ORAS
M1 | GKEST | 10212908 | 2016-12-31 | 2017-01-06 | 4 | LOW-Opportunistic | P1 | 10117976 | 3300-CMF-229 | Camera is out of focus | MELVINB | CAMERA, F20229 Fines DMS Underflow SW | B. MELVIN | NOCO ORAS
M1 | GKEST | 10212909 | 2016-12-31 | 2017-01-06 | 4 | LOW-Opportunistic | P1 | 10118024 | 3810-CMF-212 | Camera is out of focus | MELVINB | CAMERA, F20212 Maint Shop Emerg Exit D2 | B. MELVIN | NOCO ORAS
M1 | GKEST | 10212910 | 2016-12-31 |  | 4 | LOW-Opportunistic | P1 |  | 3810-CMF-213 | Camera is dirty | MELVINB | CAMERA, F20213 Proc Plant Emer Exit D2 | B. MELVIN | OSNO
M1 | GKEST | 10212911 | 2016-12-31 |  | 4 | LOW-Opportunistic | P1 |  | 3810-CMF-222 | Camera is dirty | MELVINB | CAMERA, F20222 Rec Mat Xfr OHD Proc Side | B. MELVIN | OSNO
M1 | GKEST | 10212912 | 2016-12-31 | 2017-01-06 | 4 | LOW-Opportunistic | P1 | 10117978 | 3400-CMF-007 | Camera is out of focus | MELVINB | CAMERA, F30007 Sink Screen West Pump | B. MELVIN | NOCO ORAS
M1 | GKEST | 10212913 | 2016-12-31 | 2017-01-06 | 4 | LOW-Opportunistic | P1 | 10117979 | 3400-CMF-170 | Camera is out of focus | MELVINB | CAMERA, F36170 Grease Belt Feed Bin SE | B. MELVIN | NOCO ORAS
M1 | GKEST | 10212914 | 2016-12-31 | 2017-01-06 | 4 | LOW-Opportunistic | P1 | 10118020 | 3400-CMF-182 | Camera is out of focus | MELVINB | CAMERA, F36182 4F Lifting Well | B. MELVIN | NOCO ORAS
M1 | GKEST | 10212915 | 2016-12-31 | 2017-01-06 | 4 | LOW-Opportunistic | P1 | 10117977 | 3400-CMF-002 | Camera is out of focus | MELVINB | CAMERA, F30002 Sink Scr West Mid Bin W | B. MELVIN | NOCO ORAS
M1 | GKEST | 10212916 | 2016-12-31 |  | 4 | LOW-Opportunistic | P1 |  | 3400-CMF-121 | Camera is dirty | MELVINB | CAMERA, F32121 Sink Screen East NE | B. MELVIN | OSNO
M1 | GKEST | 10212917 | 2016-12-31 |  | 4 | LOW-Opportunistic | P1 |  | 3400-CMF-105 | Camera is dirty | MELVINB | CAMERA, F32105 Sink Screen West NE | B. MELVIN | OSNO
M1 | GKEST | 10212918 | 2016-12-31 | 2017-01-06 | 4 | LOW-Opportunistic | P1 | 10118023 | 3810-CMF-207 | Camera appears to have humidity in housi | MELVINB | CAMERA, F20207 East OHD Interior View | B. MELVIN | NOCO ORAS
M1 | GKEST | 10212919 | 2016-12-31 |  | 4 | LOW-Opportunistic | P1 |  | 3810-CMF-209 | Camera is dirty | MELVINB | CAMERA, F20209 Transfer Tower Emerg Exit | B. MELVIN | OSNO
M1 | GKEST | 10212920 | 2016-12-31 | 2017-01-06 | 4 | LOW-Opportunistic | P1 | 10117973 | 3100-CMF-274 | Camera is dirty | MELVINB | CAMERA, F10274 Prim Crusher Rock Breaker | B. MELVIN | NOCO ORAS
M1 | GKEST | 10212921 | 2016-12-31 | 2017-01-06 | 4 | LOW-Opportunistic | P1 | 10117974 | 3100-CMF-277 | Camera is dirty | MELVINB | CAMERA, F10277 Prim Crusher Disch Belt | B. MELVIN | NOCO ORAS
M1 | GKEST | 10212922 | 2016-12-31 |  | 4 | LOW-Opportunistic | P1 |  | 3100-CMF-278 | Camera is dirty | MELVINB | CAMERA, F10278 Stockpile Reclaim Hopper | B. MELVIN | OSNO
M1 | GKEST | 10212923 | 2016-12-31 | 2017-04-03 | 4 | LOW-Opportunistic | P1 |  | 3100-CMF-279 | Camera is dirty | MELVINB | CAMERA, F10279 Stockpile Reclaim Feeder | B. MELVIN | NOCO
M1 | GKEST | 10212924 | 2016-12-31 |  | 4 | LOW-Opportunistic | P1 |  | 3100-CMF-280 | Camera is dirty | MELVINB | CAMERA, F10280 Primary Scrubber | B. MELVIN | OSNO
M1 | GKEST | 10212925 | 2016-12-31 |  | 4 | LOW-Opportunistic | P1 |  | 3100-CMF-283 | Camera is dirty | MELVINB | CAMERA, F20283 Plant Fd Belt | B. MELVIN | OSNO
M1 | GKEST | 10212926 | 2016-12-31 |  | 4 | LOW-Opportunistic | P1 |  | 3810-CMF-205 | Camera is dirty | MELVINB | CAMERA, F20205 Blue Area Exit | B. MELVIN | OSNO
M1 | GKEST | 10212927 | 2016-12-31 |  | 4 | LOW-Opportunistic | P1 |  | 3810-CMP-200 | Camera is dirty | MELVINB | CAMERA, P20200 Proc Plant Exterior NE | B. MELVIN | OSNO
M1 | GKEST | 10212928 | 2016-12-31 | 2017-01-06 | 4 | LOW-Opportunistic | P1 | 10118021 | 3400-CMP-167 | Camera is out of focus | MELVINB | CAMERA, P35167 3FM West PTZ | B. MELVIN | NOCO ORAS
M1 | GKEST | 10212929 | 2016-12-31 | 2017-01-06 | 4 | LOW-Opportunistic | P1 | 10118022 | 3400-CMP-172 | Issue with camera control | MELVINB | CAMERA, P36172 Underpans West PTZ | B. MELVIN | NOCO ORAS
M1 | GKEST | 10213136 | 2017-01-01 | 2017-01-13 | 2 | HIGH-Within 2 Weeks | P1 | 10118233 | 3400-BRD-016 | Bio-reader is not working | MELVINB | READER, Bio, IN, 3F Virtual Barrier | B. MELVIN | NOCO ORAS
M1 | GKEST | 10213239 | 2017-01-02 | 2017-01-13 | 1 | URGENT-Break Sched | P1 | 10118234 | 3400-SFB-001A | SFB #1 Fail | MELVINB | BOX 1, Field Security, Recovery Area GF | B. MELVIN | NOCO ORAS
M1 | GKEST | 10213871 | 2017-01-06 | 2017-01-13 | 2 | HIGH-Within 2 Weeks | P1 | 10118093 | 5200-SFB-001 | Battery fail alarm for the SFBMain Camp | MELVINB | BOX, Field Security, Luggage Screen Area | B. MELVIN | NOCO ORAS
M1 | GKEST | 10213873 | 2017-01-06 | 2017-01-13 | 2 | HIGH-Within 2 Weeks | P1 | 10118092 | 3400-SFB-004 | SFB 2nd floor battery fail alaarm | MELVINB | BOX, Field Security, Recovery Area 2F | B. MELVIN | NOCO ORAS
M1 | GKEST | 10213874 | 2017-01-06 | 2017-01-13 | 1 | URGENT-Break Sched | P1 | 20070630 | 3400-BRD-015 | Bio-reader not functioning | MELVINB | READER, Bio, IN, 2F Virtual Barrier | B. MELVIN | NOCO ORAS
M1 | GKEST | 10213875 | 2017-01-06 | 2017-01-13 | 1 | URGENT-Break Sched | P1 | 20070631 | 3400-BRD-016 | Bio reader not functioning | MELVINB | READER, Bio, IN, 3F Virtual Barrier | B. MELVIN | NOCO ORAS
M1 | GKEST | 10213883 | 2017-01-06 | 2017-01-13 | 1 | URGENT-Break Sched | P1 | 20070632 |  | Recovery overhead doors offline | MELVINB |  | B. MELVIN | NOCO ORAS
M1 | GKEST | 10214369 | 2017-01-09 | 2017-01-19 | 2 | HIGH-Within 2 Weeks | P1 | 10118076 | 3400-CMP-044 | bracket has shook loose | MELVINB | CAMERA, P30044 Ball Mill Sump PTZ | B. MELVIN | NOCO ORAS
M1 | GKEST | 10214924 | 2017-01-11 | 2017-01-15 | 1 | URGENT-Break Sched | P1 | 10118240 |  | Thermostate in the D117 Termination room | MELVINB |  | B. MELVIN | NOCO ORAS
M1 | GKEST | 10216158 | 2017-01-18 | 2017-03-24 | 2 | HIGH-Within 2 Weeks | P1 | 10118567 |  | Install bio-readers in DMS Blue Area | COULOMBEM |  | COULOMBEM | NOCO ORAS
M1 | GKEST | 10216190 | 2017-01-18 | 2017-01-25 | 1 | URGENT-Break Sched | P1 | 10118566 | 5000 | Repair of MagLocks in Export Bay | COULOMBEM |  | COULOMBEM | NOCO ORAS
M1 | GKEST | 10216310 | 2017-01-19 | 2017-01-30 | 2 | HIGH-Within 2 Weeks | P1 | 10118372 |  | Alarms on Ravens in Recovery Sort House | COULOMBEM |  | COULOMBEM | NOCO ORAS
M1 | GKEST | 10217350 | 2017-01-26 | 2017-01-30 | 1 | URGENT-Break Sched | P1 | 10118717 | 3900-SDM-001 | Overhead Door Is Opening on it's own | BARTLETTK | CONTACT, Door, GF Outer Export Bay | BARTLETTK | NOCO ORAS
M1 | GKEST | 10217633 | 2017-01-28 | 2017-01-31 | 1 | URGENT-Break Sched | P1 | 10118789 | 3400-SFB-006 | SFB Battery Replacement | BARTLETTK | BOX, Field Security, Recovery Area 4F | BART | NOCO ORAS
M1 | GKEST | 10217638 | 2017-01-28 | 2017-01-31 | 2 | HIGH-Within 2 Weeks | P1 | 10118790 | 3400-SVB-001 | Virtual Barrier Steady Alarm | BARTLETTK | BARRIER, Virtual, 1F | BARTLETTK | NOCO ORAS
M1 | GKEST | 10217639 | 2017-01-28 | 2017-01-31 | 2 | HIGH-Within 2 Weeks | P1 | 10118791 | 3400-SVB-002 | Virtual Barrier Steady Alarm | BARTLETTK | BARRIER, Virtual, 2F | BARTLETTK | NOCO ORAS
M1 | GKEST | 10217640 | 2017-01-28 | 2017-01-31 | 2 | HIGH-Within 2 Weeks | P1 | 10118792 | 3400-SVB-003 | Virtual Barrier Steady Alarm | BARTLETTK | BARRIER, Virtual, 3F | BARTLETTK | NOCO ORAS
M1 | GKEST | 10217641 | 2017-01-28 | 2017-01-31 | 2 | HIGH-Within 2 Weeks | P1 | 10118793 | 3400-SVB-004 | Virtual Barrier Steady Alarm | BARTLETTK | BARRIER, Virtual, 4F | BARTLETTK | NOCO ORAS
M1 | GKEST | 10217652 | 2017-01-28 | 2017-01-31 | 2 | HIGH-Within 2 Weeks | P1 | 10118794 | 3400-SDM-030 | Raven 1 - Door Contact | BARTLETTK | CONTACT 1, Door, 1FM Raven 1 | BARTLETTK | NOCO ORAS
M1 | GKEST | 10217653 | 2017-01-28 | 2017-01-31 | 1 | URGENT-Break Sched | P1 | 10118795 | 3400-SDM-036 | Raven 3 - Door Contacts | BARTLETTK | CONTACT 1, Door, 1FM Raven 3 | BARTLETTK | NOCO ORAS
M1 | GKEST | 10217842 | 2017-01-29 | 2017-01-31 | 1 | URGENT-Break Sched | P1 | 10118796 | 3400-SDM-033 | Raven 2 - Door Contact | BARTLETTK | CONTACT 1, Door, 1FM Raven 2 | BARTLETTK | NOCO ORAS
M1 | GKEST | 10217843 | 2017-01-29 | 2017-02-16 | 1 | URGENT-Break Sched | P1 | 10118900 | 3400-SDM-039 | Raven 4 - Door Contact | BARTLETTK | CONTACT 1, Door, 1FM Raven 4 | BARTLETTK | NOCO ORAS
M1 | GKEST | 10217872 | 2017-01-29 | 2017-03-24 | 2 | HIGH-Within 2 Weeks | P1 | 10118901 | 5110-CMP-282 | Truck Shop Ext Camera Repair | BARTLETTK | CAMERA, P10282 Truck Shop | BARTLETTK | NOCO ORAS
M1 | GKEST | 10218319 | 2017-02-01 | 2017-02-04 | 1 | URGENT-Break Sched | P1 | 20071019 | 3400-BRD-015 | Rec 2F, 3F, 4F BIO Readers Reset | BARTLETTK | READER, Bio, IN, 2F Virtual Barrier | BARTLETTK | NOCO ORAS
M1 | GKEST | 10220782 | 2017-02-16 | 2017-03-08 | 2 | HIGH-Within 2 Weeks | P1 | 10119418 | 3100-SFB-002 | Install Heater in 3100-SFB-002 | BARTLETTK | BOX, Field Security, Reclaim Area | BARTLETTK | NOCO ORAS
M1 | GKEST | 10220783 | 2017-02-16 |  | 3 | MEDIUM-Within 1 Mnth | P1 | 10119424 | 3400-SFB-005 | Install Cable Between Recovery SFBs | BARTLETTK | BOX, Field Security, Recovery Area 3F | BARTLETTK | NOPR ORAS
M1 | GKEST | 10220784 | 2017-02-16 |  | 3 | MEDIUM-Within 1 Mnth | P1 | 10119420 | 3300-SFB-001 | Install Cable Between SFB and Virtual Ba | BARTLETTK | BOX, Field Security, DMS Area | BARTLETTK | NOPR ORAS
M1 | GKEST | 10220785 | 2017-02-16 |  | 3 | MEDIUM-Within 1 Mnth | P1 | 10119421 | 3400-SFB-003 | Install Cable Between SFB and Virtual Ba | BARTLETTK | BOX, Field Security, Recovery Area 1F | BARTLETTK | NOPR ORAS
M1 | GKEST | 10220786 | 2017-02-16 |  | 3 | MEDIUM-Within 1 Mnth | P1 | 10119422 | 3400-SFB-004 | Install Cable Between SFB and Virtual Ba | BARTLETTK | BOX, Field Security, Recovery Area 2F | BARTLETTK | NOPR ORAS
M1 | GKEST | 10220787 | 2017-02-16 |  | 3 | MEDIUM-Within 1 Mnth | P1 | 10119423 | 3400-SFB-005 | Install Cable Between SFB and Virtual Ba | BARTLETTK | BOX, Field Security, Recovery Area 3F | BARTLETTK | NOPR ORAS
M1 | GKEST | 10220788 | 2017-02-16 |  | 3 | MEDIUM-Within 1 Mnth | P1 | 10119425 | 3400-SFB-006 | Install Cable Between SFB and Virtual Ba | BARTLETTK | BOX, Field Security, Recovery Area 4F | BARTLETTK | NOPR ORAS
M1 | GKEST | 10220825 | 2017-02-17 | 2017-04-03 | 2 | HIGH-Within 2 Weeks | P1 | 10119419 | 3400-SVB-004 | Virtual Barrier is Faulted - to be repla | BARTLETTK | BARRIER, Virtual, 4F | BARTLETTK | NOCO ORAS
M1 | GKEST | 10220970 | 2017-02-18 |  | 2 | HIGH-Within 2 Weeks | P1 | 10119428 | 3400-SDM-030 | Raven Switches | BARTLETTK | CONTACT 1, Door, 1FM Raven 1 | BARTLETTK | NOPR ORAS
M1 | GKEST | 10221020 | 2017-02-18 | 2017-02-20 | 2 | HIGH-Within 2 Weeks | P1 | 10119427 | 3400-CMF-058 | Main and Grease Glovebox Cameras | BARTLETTK | CAMERA, F30058 Srt Hse Glovebox Int 1 | BARTLETTK | NOCO ORAS
M1 | GKEST | 10221041 | 2017-02-18 |  | 2 | HIGH-Within 2 Weeks | P1 | 10119406 | 3400-CRD-008 | West DMS Card Readers | BARTLETTK | READER, Card, IN, DMS Virual Barrier 1 | BARTLETTK | NOPR ORAS
M1 | GKEST | 10221062 | 2017-02-18 |  | 2 | HIGH-Within 2 Weeks | P1 | 10119426 |  | XRay Alarm Testing Results | BARTLETTK |  | BARTLETTK | NOPR ORAS
M1 | GKEST | 10221949 | 2017-02-23 |  | 2 | HIGH-Within 2 Weeks | P1 | 10119600 |  | Dorm A3 Rear emergency light out | MELVINB |  | B. MELVIN | NOPR ORAS
M1 | GKEST | 10222477 | 2017-02-27 | 2017-03-01 | 1 | URGENT-Break Sched | P1 | 10119577 | 5300-BRD-001 | Bio reader not working at sorthouse | MELVINB | READER, Bio, IN, Red Entrance Door 1 | B. MELVIN | NOCO ORAS
M1 | GKEST | 10222479 | 2017-02-27 | 2017-02-27 | 4 | LOW-Opportunistic | P1 |  |  | Fluorescent tube burnt out | MELVINB |  | B. MELVIN | NOCO
M1 | GKEST | 10222730 | 2017-03-01 |  | 3 | MEDIUM-Within 1 Mnth | P1 |  | 3400-CMF-058 | Camera is dirty | MELVINB | CAMERA, F30058 Srt Hse Glovebox Int 1 | B. MELVIN | OSNO
M1 | GKEST | 10222844 | 2017-03-01 | 2017-03-13 | 2 | HIGH-Within 2 Weeks | P1 | 10119714 | 4900-SFB-001 | Breaker trips during power outages | MELVINB | BOX, Field Security, IT Server Room | B. MELVIN | NOCO ORAS
M1 | GKEST | 10222845 | 2017-03-01 |  | 2 | HIGH-Within 2 Weeks | P1 | 10119713 | 3400-SFB-001 | Breaker trips during power outages | MELVINB | BOX, Field Security, Recovery Sort House | B. MELVIN | NOPR ORAS
M1 | GKEST | 10222869 | 2017-03-02 | 2017-03-08 | 2 | HIGH-Within 2 Weeks | P1 | 10119707 | 3400-BRD-017 | Bio reader not working | MELVINB | READER, Bio, IN, 4F Virtual Barrier | B. MELVIN | NOCO ORAS
M1 | GKEST | 10222870 | 2017-03-02 | 2017-03-08 | 2 | HIGH-Within 2 Weeks | P1 | 10119706 | 3400-BRD-015 | Bio reader not working | MELVINB | READER, Bio, IN, 2F Virtual Barrier | B. MELVIN | NOCO ORAS
M1 | GKEST | 10222871 | 2017-03-01 |  | 3 | MEDIUM-Within 1 Mnth | P1 |  | 3400-CMF-059 | Camera is dirty | MELVINB | CAMERA, F30059 Srt Hse Glovebox Int 2 | B. MELVIN | OSNO
M1 | GKEST | 10222872 | 2017-03-01 |  | 3 | MEDIUM-Within 1 Mnth | P1 |  | 3400-CMF-060 | Camera is dirty | MELVINB | CAMERA, F30060 Srt Hse Glovebox Int 3 | B. MELVIN | OSNO
M1 | GKEST | 10222873 | 2017-03-01 |  | 3 | MEDIUM-Within 1 Mnth | P1 |  | 3400-CMF-063 | Camera is dirty | MELVINB | CAMERA, F30063 Srt Hse Glovebox Int 6 | B. MELVIN | OSNO
M1 | GKEST | 10222875 | 2017-03-01 |  | 3 | MEDIUM-Within 1 Mnth | P1 |  | 3400-CMF-116 | Camera is dirty | MELVINB | CAMERA, F32116 Srt Hse Grease Belt Glvbx | B. MELVIN | OSNO
M1 | GKEST | 10222971 | 2017-03-02 | 2017-03-08 | 2 | HIGH-Within 2 Weeks | P1 | 10119705 |  | investigate thermostat | MELVINB |  | B. MELVIN | NOCO ORAS
M1 | GKEST | 10223272 | 2017-03-04 |  | 3 | MEDIUM-Within 1 Mnth | P1 | 10119764 |  | Ballast requires replacing | MELVINB |  | B. MELVIN | NOPR ORAS
M1 | GKEST | 10223960 | 2017-03-09 |  | 2 | HIGH-Within 2 Weeks | P1 |  |  | 4th floor cameras off-line | MELVINB |  | B. MELVIN | OSNO
M1 | GKEST | 10227069 | 2017-03-26 | 2017-04-08 | 2 | HIGH-Within 2 Weeks | P1 | 10120395 | 3100-CMF-281 | Camera requires to be repositioned | MELVINB | CAMERA, F10281 Second Crusher Fd Belt | B. MELVIN | NOCO ORAS
M1 | GKEST | 10227588 | 2017-03-31 | 2017-04-03 | 2 | HIGH-Within 2 Weeks | P1 | 10120485 | 3400-BRD-017 | Bio reader not functioning | MELVINB | READER, Bio, IN, 4F Virtual Barrier | B. MELVIN | NOCO ORAS

## Sheet1 (2)
Notifictn type | Main WorkCtr | Notification | Created on | Completn date | Priority | Priority | PriorityType | Order | Sort field | Description | Created by | Description | Reported by | System status
M1 | VSEE1 | 10215218 | 2017-01-14 | 2017-01-16 | 1 | URGENT-Break Sched | P1 | 10118305 |  | IT controller offline | MILLSJ |  | JOHN MILLS | NOCO ORAS
M1 | VSEE1 | 10217335 | 2017-01-26 | 2017-02-01 | 1 | URGENT-Break Sched | P1 | 20070897 |  | SADE 1 Technical support | HORTHO |  | HORTH O. | NOCO ORAS
M1 | VSEE1 | 10219674 | 2017-02-10 |  | 1 | URGENT-Break Sched | P1 | 10119337 | 3400-BRD-301 | Recovery - 3rd Floor BIO Reader errors. | BARTLETTK | REC 3RD FL VIRT BAR ENT BIO CARD READER | BARTLETTK | NOPR ORAS
M1 | VSEE1 | 10227744 | 2017-04-01 |  | 1 | URGENT-Break Sched | P1 | 10120694 | 3400-SDM-155 | Investigate Line Error on Vault door SDM | CVETKOVSKIZ | VAULT DR CONTACT | CVETKOVSKIZ | NOPR ORAS
M1 | VSEE1 | 10227923 | 2017-04-02 | 2017-04-04 | 1 | URGENT-Break Sched | P1 | 20071904 | 5300-BRD-203 | Bio-reader has makfunctioned. | HORTHO | OBSERVATION RM ENT BIO CARD READER | HORTHO | NOCO ORAS
M1 | VSEE1 | 10219100 | 2017-02-07 |  | 1 | URGENT-Break Sched | P1 | 10119040 | 5300-SVR-211 | Cabinet Network Cables | HORTHO | PS EQUIP PRI CCTV SERVER | HORTH O. | NOPR ORAS
M1 | VSEE1 | 10222489 | 2017-02-27 | 2017-03-02 | 3 | MEDIUM-Within 1 Mnth | P1 |  |  | Gym Penthouse Security Systems | BARTLETTK |  | BARTLETTK | NOCO
M1 | VSEE1 | 10211610 | 2016-12-22 | 2017-01-03 | 3 | MEDIUM-Within 1 Mnth | P1 | 10117768 |  | Blue Zone-Coarse Screen Prep PTZ camera | QUACHEGANJ |  | JUNEQ | NOCO ORAS
M1 | VSEE1 | 10211611 | 2016-12-22 | 2017-01-03 | 3 | MEDIUM-Within 1 Mnth | P1 | 10117767 |  | Blue Zone-Coarse Floats PTZ camera | QUACHEGANJ |  | JUNEQ | NOCO ORAS
M1 | VSEE1 | 10211612 | 2016-12-22 | 2017-01-03 | 3 | MEDIUM-Within 1 Mnth | P1 | 10117766 |  | Blue Zone-Fines Floats PTZ camera | QUACHEGANJ |  | JUNEQ | NOCO ORAS
M1 | VSEE1 | 10211613 | 2016-12-22 | 2017-01-03 | 3 | MEDIUM-Within 1 Mnth | P1 | 10117769 |  | Blue Zone - Degrit Screen PTZ camera | QUACHEGANJ |  | JUNEQ | NOCO ORAS
M1 | VSEE1 | 10211642 | 2016-12-22 |  | 3 | MEDIUM-Within 1 Mnth | P1 | 10117775 |  | 6th Floor DMS Entry camera - no video | QUACHEGANJ |  | QUACHEGANJ | NOPR ORAS
M1 | VSEE1 | 10211616 | 2016-12-22 | 2017-01-29 | 3 | MEDIUM-Within 1 Mnth | P1 | 10117771 | 3400-CMF-318 | Rejects Feed Belt Recovery outside tower | QUACHEGANJ | REC 3RD FL FIXED CAMERA | QUACHEGANJ | NOCO ORAS
M1 | VSEE1 | 10211640 | 2016-12-22 | 2017-02-05 | 3 | MEDIUM-Within 1 Mnth | P1 | 10117776 | 3400-CMF-318 | South Dewatering Screen camera | QUACHEGANJ | REC 3RD FL FIXED CAMERA | QUACHEGANJ | NOCO ORAS
M1 | VSEE1 | 10211641 | 2016-12-22 | 2017-01-13 | 3 | MEDIUM-Within 1 Mnth | P1 | 10117777 | 3400-CMF-411 VR4-F-411 | Emerg Exit camera | QUACHEGANJ | REC 4TH FL FIXED CAMERA EMERG EXIT | JUNEQ | NOCO ORAS
M1 | VSEE1 | 10211643 | 2016-12-22 | 2017-01-13 | 3 | MEDIUM-Within 1 Mnth | P1 | 10117778 | 3400-CMP-502 VR5-P-502 | REDS 1&3 PTZ camera | QUACHEGANJ | REC 5TH FL PTZ CAMERA FINES/COARSE REDS | JUNEQ | NOCO ORAS
M1 | VSEE1 | 10225634 | 2017-03-19 | 2017-04-14 | 3 | MEDIUM-Within 1 Mnth | P1 | 10120253 | 3400-CMP-503 VR5-P-503 | Condensation build up inside dome | QUACHEGANJ | REC 5TH FL PTZ CAMERA REDS 1&3 | QUACHEGANJ | NOCO ORAS
M1 | VSEE1 | 10218196 | 2017-02-01 |  | 3 | MEDIUM-Within 1 Mnth | P1 | 10118906 | 3400-CMP-601 VRD-P-601 | Camera service - blurry & shaky. | HORTHO | REC 6TH FL PTZ CAMERA DMS Overview | HORTHO | NOPR ORAS
M1 | VSEE1 | 10224117 | 2017-03-09 |  | 3 | MEDIUM-Within 1 Mnth | P1 | 10120091 | 3400-SDM-217 | Lenel alarm system did not activate | QUACHEGANJ | CRS SEC 3430-XR-010 DR CONTACT | JUNE Q | NOPR ORAS
M1 | VSEE1 | 10211585 | 2016-12-22 | 2017-01-03 | 3 | MEDIUM-Within 1 Mnth | P1 | 10117772 | 3730-CMP-001 | External PK Tower camera dirty/hazy | QUACHEGANJ | P.K DISPOSAL PTZ CAMERA | JUNEQ | NOCO ORAS
M1 | VSEE1 | 10211586 | 2016-12-22 | 2017-01-03 | 3 | MEDIUM-Within 1 Mnth | P1 | 10117773 | 3900-CMF-001 | E Emerg P5 Exit camera | QUACHEGANJ | EMERGENCY EXIT DRS FIXED CAMERA | JUNEQ | NOCO ORAS
M1 | VSEE1 | 10211588 | 2016-12-22 | 2017-01-03 | 3 | MEDIUM-Within 1 Mnth | P1 | 10117774 | 3900-CMF-011 | Magnetic Separator West camera | QUACHEGANJ | MAGNETIC SEPARATOR 1 FIXED CAMERA | JUNEQ | NOCO ORAS
M1 | VSEE1 | 10211589 | 2016-12-22 | 2017-01-03 | 3 | MEDIUM-Within 1 Mnth | P1 | 10117770 | 3900-CMF-015 VIC.PPT.F.2.6.270 | B Mod Coarse Cyclone camera | QUACHEGANJ | B MOD COARSE CYCLONE FIXED CAMERA | JUNEQ | NOCO ORAS
M1 | VSEE1 | 10211617 | 2016-12-22 |  | 3 | MEDIUM-Within 1 Mnth | P1 | 10117801 | 3900-CMF-034 | MOD C Fines Sinks Screen camera | QUACHEGANJ | Mod C Fines Sinks Screen FIXED CAMERA | QUACHEGANJ | NOPR ORAS
M1 | VSEE1 | 10211618 | 2016-12-22 |  | 3 | MEDIUM-Within 1 Mnth | P1 | 10117800 | 3900-CMF-034 | MOD B Coarse Sinks Screen camera | QUACHEGANJ | Mod C Fines Sinks Screen FIXED CAMERA | QUACHEGANJ | NOPR ORAS
M1 | VSEE1 | 10211619 | 2016-12-22 |  | 3 | MEDIUM-Within 1 Mnth | P1 | 10117802 | 3900-CMF-034 | MOD A Coars Sinks Screen camera | QUACHEGANJ | Mod C Fines Sinks Screen FIXED CAMERA | QUACHEGANJ | NOPR ORAS
M1 | VSEE1 | 10211053 | 2016-12-19 | 2017-03-11 | 3 | MEDIUM-Within 1 Mnth | P1 | 10118236 | 3900-SSL-002 | Replace indicating lights, mandoor P4. | MILLSJ | BLUE AREA LAYDOWN AREA SECURITY STROBE | MILLSJ | NOCO ORAS
M1 | VSEE1 | 10216399 | 2017-01-20 | 2017-04-15 | 3 | MEDIUM-Within 1 Mnth | P1 | 10118525 | 5300-SVR-215 | IT server room door missing sensor. | MILLSJ | PS EQUIP PRI REPORT SERVER | MILLSJ | NOCO ORAS
M1 | VSEE1 | 10203014 | 2016-11-12 | 2017-02-08 | 4 | Medium | PM | 10116500 |  | CMT - Tank - Readers - Offline | HORTHO |  | HORTHO | NOCO ORAS
M1 | VSEE1 | 10197999 | 2016-10-11 | 2016-11-13 | 4 | Medium | PM | 20069372 |  | Dirty Camera's total - 7 | HORTHO |  | HORTH O. | NOCO ORAS
M1 | VSEE1 | 10195419 | 2016-09-27 | 2016-09-29 | 4 | Medium | PM |  |  | Exterior Recovery Export Bay card reader | QUACHEGANJ |  | JUNE Q | NOCO
M1 | VSEE1 | 10205421 | 2016-11-28 | 2016-11-29 | 4 | Medium | PM |  |  | Re-wire CM Tank security board | MILLSJ |  | JOHN MILLS | NOCO
M1 | VSEE1 | 10189660 | 2016-09-06 | 2016-11-07 | 4 | Medium | PM | 10114761 |  | BSP Overhead Door constantly alarming | QUACHEGANJ |  | JUNE Q | NOCO NOPT ORAS
M1 | VSEE1 | 10189661 | 2016-09-06 | 2016-09-16 | 4 | Medium | PM | 10114733 |  | change ptz home positions | QUACHEGANJ |  | JUNE Q | NOCO NOPT ORAS
M1 | VSEE1 | 10184972 | 2016-04-22 | 2016-05-03 | 4 | Medium | PM | 20066984 |  | Camera repair | HORTHO |  | HORTH | NOCO ORAS
M1 | VSEE1 | 10186442 | 2016-06-05 | 2016-06-08 | 4 | Medium | PM | 10112789 | 5300-BU-072 | Camera VIC.RPT.P.3.6.311 Pneumo/PK | QUACHEGANJ | Facility, Protect. Services Control Room | JUNE Q | NOCO ORAS
M1 | VSEE1 | 10198010 | 2016-10-11 | 2016-10-29 | 4 | Medium | PM | 10115648 | 3400-CMF-422 | Camera Adjustment | HORTHO | REJECTS FEED BELT FIXED CAMERA | HORTH O. | NOCO ORAS
M1 | VSEE1 | 10197997 | 2016-10-11 | 2016-11-06 | 4 | Medium | PM | 10115646 | 3400-CMF-604 VR6-F-604 | 6th floor DMS Entry - Camera repair | HORTHO | 6th FLOOR ENTRY/STAIRS TO KOFIXED CAMERA | HORTH O. | NOCO NOPT ORAS
M1 | VSEE1 | 10192701 | 2016-09-15 | 2017-02-18 | 4 | Medium | PM | 10115044 | 3400-CMP-103 VD-P-103-DTC | Mask vault dials on cleaning room camera | HORTHO | CLEANING FACILITY PTZ CAMERA N/E | HORTHO | NOCO ORAS
M1 | VSEE1 | 10184971 | 2016-04-22 | 2016-05-03 | 4 | Medium | PM | 20066983 | 3400-CMP-155 VD-P-155-DTC | PTZ Camera repair PS Cleaning Room | HORTHO | CLEANING FACILITY PTZ CAMERA N/W | HORTH | NOCO ORAS
M1 | VSEE1 | 10201809 | 2016-11-06 | 2016-12-15 | 4 | Medium | PM | 10116302 | 3400-CMP-157 VD-P-157-DTC | Fading of PTZ camera - in corners | HORTHO | CLEANING FACILITY PTZ CAMERA S/E | HORTH O. | NOCO ORAS
M1 | VSEE1 | 10197121 | 2016-10-07 | 2016-10-29 | 4 | Medium | PM | 10115541 | 3400-SDM-521 | Alarm malfunction - repeating continual | HORTHO | CRS RED MACHINE 3430-MS-004 DR CONTACT | HORTH O. | NOCO ORAS
M1 | VSEE1 | 10197998 | 2016-10-11 | 2016-11-08 | 4 | Medium | PM | 10115654 | 3900-CMF-015 VIC.PPT.F.2.6.270 | VIC.PPT.F.2.6.270 - Fines Cyclone | HORTHO | B MOD COARSE CYCLONE FIXED CAMERA | HORTH O. | NOCO NOPT ORAS
M1 | VSEE1 | 10204962 | 2016-11-24 | 2016-12-09 | 4 | Medium | PM | 10117048 | 3900-CRD-003 | Blue Airlock | MILLSJ | BLUE AREA LAYDOWN AREA CARD READER | JOHN MILLS | NOCO ORAS
M1 | VSEE1 | 10205241 | 2016-11-26 | 2016-12-07 | 4 | Medium | PM | 10117042 | 3900-CRD-003 | photo sensors need to be readjusted | MILLSJ | BLUE AREA LAYDOWN AREA CARD READER | JOHN MILLS | NOCO ORAS
M1 | VSEE1 | 10206852 | 2016-12-06 | 2016-12-15 | 4 | Medium | PM | 10117233 | 5300-CMF-201 | Camera service - VIC.PEX.F.2.2.034 | HORTHO | BLUE AREA EXIT VEST DR 1 FIXED CAMERA | HORTH O. | NOCO ORAS
M1 | VSEE1 | 10189222 | 2016-08-25 | 2016-09-09 | 4 | Medium | PM | 10114375 | 5300-IND-202G | RED light burnt out | QUACHEGANJ | RED AREA EXIT VEST DR 1 INDICATOR LIGHT | JUNE Q | NOCO ORAS
M1 | VSEE1 | 10201478 | 2016-11-03 | 2016-11-06 | 4 | Medium | PM | 20069565 | 5300-IND-211G | North dressing room PLC not resetting | HORTHO | DRESSING RM 1 ENT DR INDICATOR LIGHT | HORTH O. | NOCO ORAS
M1 | VSEE1 | 10195114 | 2016-09-26 | 2016-10-25 | 4 | Medium | PM | 10115268 | 5300-ML-203 | Re-align mag lock on door frame to door. | QUACHEGANJ | BLUE AREA EXIT VEST DR 2 ELEC-MAG LOCK | JUNE Q | NOCO ORAS
M1 | VSEE1 | 10219661 | 2017-02-09 |  | 4 | LOW-Opportunistic | P1 | 10119109 |  | Glovebox Camera Replacement | BARTLETTK |  | BARTLETTK | NOPR ORAS
M1 | VSEE1 | 10218758 | 2017-02-04 | 2017-02-06 | 4 | LOW-Opportunistic | P1 | 20071076 |  | Men's washroom - florescent light | HORTHO |  | HORTH O. | NOCO ORAS
M1 | VSEE1 | 10226737 | 2017-03-23 | 2017-03-25 | 4 | LOW-Opportunistic | P1 |  |  | I.M. Housekeeping-cables trip hazard | HORTHO |  | HORTH O. | DLFL NOCO
M1 | VSEE1 | 10182432 | 2016-02-14 | 2016-02-15 | 5 | Low | PM | 10110568 |  | Replace fluorescent light in washroom | QUACHEGANJ |  | QUACHEGANJ | NOCO ORAS
M1 | VSEE1 | 10199620 | 2016-10-21 | 2016-10-22 | 5 | Low | PM |  |  | Telephone Luggage area | MILLSJ |  | JOHN MILLS | NOCO
M1 | VSEE1 | 10186443 | 2016-06-05 | 2016-06-05 | 5 | Low | PM |  | 5300-BU-072 | Camera VIC.RPT.P.3.6.311 Pneumo/PK | QUACHEGANJ | Facility, Protect. Services Control Room | JUNE Q | NOCO
M1 | VSEE1 | 10186451 | 2016-06-05 | 2016-06-17 | 5 | Low | PM | 10112867 | 5300-BU-072 | PCC Monitor #2 image frozen | QUACHEGANJ | Facility, Protect. Services Control Room | JUNE Q | NOCO ORAS
M1 | VSEE1 | 10186452 | 2016-06-05 | 2016-06-08 | 5 | Low | PM | 10112790 | 5300-BU-072 | Recovery N/W Emerg Exit Door in alarm. | QUACHEGANJ | Facility, Protect. Services Control Room | JUNE Q | NOCO ORAS
M1 | VSEE1 | 10206058 | 2016-12-01 | 2016-12-13 | 5 | Low | PM | 10117154 | 3400-CMF-302 VR3-F-302 | Picture is black | QUACHEGANJ | REC 3RD FL FIXED CAMERA FINES/MIDS RECON | QUACHEGANJ | NOCO ORAS
M1 | VSEE1 | 10206057 | 2016-12-01 | 2017-01-13 | 5 | Low | PM | 10117153 | 5300-CMF-209 | Red Exit Vestibule losng camera picture. | QUACHEGANJ | RED AREA EXIT VEST FIXED CAMERA | QUACHEGANJ | NOCO ORAS
M2 | VSEE1 | 10193137 | 2016-09-17 | 2016-09-19 | 5 | Low | PM | 10114991 | 3900-BRD-002 | Sensor recalibration or Unit replacement | HORTHO | PCS Server Room Bio Reader | HORTH O. | NOCO ORAS
M1 | VSEE1 | 10188647 | 2016-08-09 | 2016-08-11 | 1 | Immediate | PM | 10114085 |  | NVR - 29 failure | QUACHEGANJ |  | JUNE Q | NOCO ORAS
M1 | VSEE1 | 10215412 | 2017-01-15 | 2017-01-15 | 2 | HIGH-Within 2 Weeks | P1 |  |  | printer not connect to network | MILLSJ |  | JOHN MILLS | NOCO
M1 | VSEE1 | 10218189 | 2017-01-31 | 2017-04-01 | 2 | HIGH-Within 2 Weeks | P1 | 10118841 | 3811-XR-002 | Noise coming from X-Ray - fan | HORTHO | X-Ray Machine, Export Bay PCC | HORTH O. | NOCO ORAS
M1 | VSEE1 | 10220827 | 2017-02-17 |  | 2 | HIGH-Within 2 Weeks | P1 | 10119345 | 3400-CMF-115 VRG-F-115 | VIC-RPT.F.3.1.118 Pneumodrier Transfer | MILLSJ | GROUND FL FIXED CAMERA Pneumo Xfer Pipes | JOHN MILLS | NOPR ORAS
M1 | VSEE1 | 10225609 | 2017-03-20 |  | 2 | HIGH-Within 2 Weeks | P1 | 20071776 | 3400-CMF-209 VR2-F-209 | VIC.RTR.F.3.2.062 distorted image again | QUACHEGANJ | REC 2ND FL FIXED CAMERA FINES/MIDS CHUTE | QUACHEGANJ | NOPR ORAS
M1 | VSEE1 | 10211110 | 2016-12-19 | 2017-02-15 | 2 | HIGH-Within 2 Weeks | P1 | 10117758 | 3400-CMF-607 VR6-F-607 | Re-position camera - sizing room | MILLSJ | REC 6FL FIXED CAMERA SIZ SCRN FEEDER | MILLSJ | NOCO ORAS
M1 | VSEE1 | 10217620 | 2017-01-28 |  | 2 | HIGH-Within 2 Weeks | P1 | 20070948 | 3400-SDM-155 | Vault gate DSM defective | HORTHO | VAULT DR CONTACT | HORTH O. | NOPR ORAS
M1 | VSEE1 | 10207416 | 2016-12-09 | 2016-12-21 | 2 | HIGH-Within 2 Weeks | P1 | 10117343 | 5300-CMF-008 | VIC.REX.F.3.2.014 - Red Exit Vestibule | HORTHO | RED AREA ENT VEST 1 FIXED CAMERA | HORTH O. | NOCO ORAS
M1 | VSEE1 | 10228131 | 2017-04-03 |  | 2 | HIGH-Within 2 Weeks | P1 | 10120693 | V001530 | Investigate alarm code. | CVETKOVSKIZ | Workstation 2, PSO, PCC, Lenel, Nice | CVETKOVSKIZ | NOPR ORAS
M1 | VSEE1 | 10221048 | 2017-02-18 | 2017-02-28 | 2 | HIGH-Within 2 Weeks | P1 | 10119402 | 3900-CRD-118 | Process Plant Recirc conveyor | MILLSJ | Recirc Conv #1 Access Tube PP Card Readr | JOHN MILLS | NOCO ORAS
M1 | VSEE1 | 10181279 | 2016-01-22 | 2016-01-30 | 3 | High | PM | 10109915 |  | VIC.RCL.P.3.1.015 DTC CLEANING N/W - 244 | QUACHEGANJ |  | JUNE Q | NOCO ORAS
M1 | VSEE1 | 10198063 | 2016-10-12 | 2016-10-20 | 3 | High | PM | 10115653 |  | PSO Women's washroom - lights burnt out | HORTHO |  | HORTH O. | NOCO ORAS
M1 | VSEE1 | 10198898 | 2016-10-18 | 2016-10-31 | 3 | High | PM | 10115806 |  | I-Robot Vacuum - Troubleshoot | HORTHO |  | HORTH O. | NOCO ORAS
M1 | VSEE1 | 10198367 | 2016-10-14 | 2016-11-17 | 3 | High | PM | 10115659 |  | Luggage phone - cable connection issue | HORTHO |  | HORTH O. | NOCO ORAS
M1 | VSEE1 | 10181023 | 2016-01-15 | 2016-01-22 | 3 | High | PM | 10109799 |  | Change indicator light bulb | QUACHEGANJ |  | JUNE Q | NOCO ORAS
M1 | VSEE1 | 10195884 | 2016-09-29 | 2016-10-29 | 3 | High | PM | 10115394 |  | VIC.RTR.F.3.2.062 Fines/Mids Chute | QUACHEGANJ |  | JUNE Q | NOCO ORAS
M1 | VSEE1 | 10192400 | 2016-09-14 | 2016-09-19 | 3 | High | PM | 10114888 | 3321-CM-002 | Camera connectivity-interminttent | HORTHO | Camera, Process | HORTH O. | NOCO ORAS
M1 | VSEE1 | 10198708 | 2016-10-17 | 2017-01-13 | 3 | High | PM | 20069399 | 3400-CMP-105 VRG-P-105 | Camera repair - Blue image displaying | HORTHO | GROUND FL PTZ CAMERA PNEUMO/PK | HORTH O. | NOCO ORAS
M1 | VSEE1 | 10196788 | 2016-10-04 | 2016-10-10 | 3 | High | PM | 10115499 | 3400-SDM-156 | Lenel alarm for Red Vault inner gate | QUACHEGANJ | VAULT DR CONTACT | JUNE Q | NOCO ORAS
M1 | VSEE1 | 10189354 | 2016-08-30 | 2016-09-10 | 3 | High | PM | 10114580 | 3900-ML-002 | P 4 exit | MILLSJ | BLUE AREA LAYDOWN AREA ELEC-MAG LOCK | JOHN MILLS | NOCO ORAS
M1 | VSEE1 | 10191809 | 2016-09-13 | 2016-09-19 | 3 | High | PM | 20068880 | 3900-CMP-124 VIC.PPT.F.2.4.327 | Camera repair - DMS - Blue - 4th floor | HORTHO | DMS Access 5th & 6th East Fixed CAMERA | HORTH O. | NOCO ORAS
M1 | VSEE1 | 10198016 | 2016-10-11 | 2016-10-15 | 3 | High | PM | 10115599 | 5300-BRD-250 | Card reader - Amber light remaining on | HORTHO | Valuation Room Exterior BIO CARD READER | HORTH O. | NOCO ORAS
M2 | VSEE1 | 10190019 | 2016-09-10 | 2016-10-11 | 3 | High | PM | 20068647 | 2300-CMP-001 VE-P-3014 | repair PTZ camera at airport - security | HORTHO | AIRPORT PTZ CAMERA VIC.P.1.1.114 | HORTH O. | NOCO ORAS